## User Stories
# | Epic | User Story | As a... | I want to... | So that... | Priority | Story Points | Status
1 | Authentication | User Registration | Guest | register with email and password | I can access the platform | Must Have | 3 | To Do
2 | Authentication | User Login | Registered User | log in with email and password | I can use my account | Must Have | 2 | To Do
3 | Authentication | JWT Token Refresh | Logged-in User | automatically refresh my session token | I stay logged in without re-entering credentials | Must Have | 3 | To Do
4 | Authentication | Logout | Logged-in User | log out from the platform | my session is terminated securely | Must Have | 1 | To Do
5 | Authentication | View & Edit Profile | Logged-in User | update my name, phone, and avatar | my profile info stays current | Should Have | 2 | To Do
6 | Car Management | Add Car Listing | Car Owner | add my car with brand, model, year, fuel type, transmission, price per day and deposit | I can rent it out to others | Must Have | 5 | To Do
7 | Car Management | Upload Car Photos | Car Owner | upload multiple photos for my car listing | renters can see what the car looks like | Must Have | 3 | To Do
8 | Car Management | Set Car Location | Car Owner | set the pickup location (address/coordinates) for my car | renters know where to pick it up | Must Have | 2 | To Do
9 | Car Management | Edit Car Listing | Car Owner | edit my car's details and price | the listing stays accurate | Must Have | 3 | To Do
10 | Car Management | Delete Car Listing | Car Owner | delete my car listing | it is no longer visible to renters | Must Have | 2 | To Do
11 | Car Management | Browse Car Listings | Renter | browse available cars with photos, price, and location | I can choose the right car | Must Have | 5 | To Do
12 | Car Management | Filter Cars | Renter | filter cars by fuel type, transmission, price range and location | I find cars that match my needs | Should Have | 4 | To Do
13 | Availability | Set Car Availability | Car Owner | mark dates when my car is available or unavailable | renters only see accurate availability | Must Have | 4 | To Do
14 | Availability | View Car Availability Calendar | Renter | see a calendar of available dates for a car | I can plan my rental dates | Must Have | 3 | To Do
15 | Bookings | Create Booking Request | Renter | send a booking request for specific dates | I can reserve a car | Must Have | 5 | To Do
16 | Bookings | Approve Booking | Car Owner | approve or reject a booking request | I control who rents my car | Must Have | 4 | To Do
17 | Bookings | View My Bookings | Renter | see all my current and past bookings | I can track my rental history | Must Have | 3 | To Do
18 | Bookings | View Booking Requests | Car Owner | see all booking requests for my cars | I can manage incoming requests | Must Have | 3 | To Do
19 | Bookings | Calculate Total Price | Renter | see total rental price and deposit before confirming | I know the full cost upfront | Must Have | 2 | To Do
20 | Bookings | Cancel Booking | Renter | cancel a pending booking request | I can change my plans | Should Have | 3 | To Do
21 | Reviews | Leave Review for Car | Renter | leave a rating and comment for a car after a completed booking | other renters can make informed decisions | Should Have | 3 | To Do
22 | Reviews | Leave Review for Renter | Car Owner | leave a rating and comment for a renter after a completed booking | other owners can see renter reputation | Should Have | 3 | To Do
23 | Reviews | View Car Reviews | Renter | see all reviews for a specific car | I can evaluate the car quality | Should Have | 2 | To Do
24 | Reviews | View User Reviews | Car Owner / Renter | see reviews left about a user | I can evaluate trustworthiness | Should Have | 2 | To Do
25 | Admin | Block User | Admin | block a user account | bad actors cannot use the platform | Must Have | 2 | To Do
26 | Admin | View All Users | Admin | view all registered users | I can monitor and manage the platform | Must Have | 2 | To Do
27 | Admin | View All Bookings | Admin | view all bookings across the platform | I can resolve disputes or issues | Should Have | 2 | To Do

## API Endpoints
# | Epic | Endpoint | Method | Description | Request Body / Params | Response (Success) | Auth Required | Status Code
1 | Authentication | POST /api/auth/register | POST | Register new user | { email, password, first_name, last_name, phone? } | { id, email, first_name, last_name, access_token, refresh_token } | No | 201
2 | Authentication | POST /api/auth/login | POST | Login with email & password | { email, password } | { access_token, refresh_token, user: { id, email, first_name, avatar_url } } | No | 200
3 | Authentication | POST /api/auth/refresh | POST | Refresh access token | { refresh_token } | { access_token, refresh_token } | No | 200
4 | Authentication | POST /api/auth/logout | POST | Revoke refresh token | { refresh_token } | { message: 'Logged out successfully' } | Yes | 200
5 | Authentication | GET /api/users/me | GET | Get current user profile | Header: Authorization: Bearer <token> | { id, email, first_name, last_name, phone, avatar_url, created_at } | Yes | 200
6 | Authentication | PATCH /api/users/me | PATCH | Update current user profile | { first_name?, last_name?, phone?, avatar_url? } | { id, email, first_name, last_name, phone, avatar_url } | Yes | 200
7 | Car Management | GET /api/cars | GET | Browse all car listings | Query: brand?, model?, fuel_type?, transmission?, price_min?, price_max?, lat?, lng?, radius? | { data: [ { id, brand, model, year, price_per_day, deposit, fuel_type, transmission, address, lat, lng, photos: [url], avg_rating } ], total, page, limit } | No | 200
8 | Car Management | GET /api/cars/:id | GET | Get single car details | Param: id (UUID) | { id, brand, model, year, price_per_day, deposit, fuel_type, transmission, description, address, lat, lng, owner: { id, first_name, avatar_url }, photos: [{ id, url, sort_order }], avg_rating } | No | 200
9 | Car Management | POST /api/cars | POST | Create new car listing | { brand, model, year, fuel_type, transmission, price_per_day, deposit, description?, address?, lat?, lng? } | { id, brand, model, year, price_per_day, deposit, owner_id, created_at } | Yes | 201
10 | Car Management | PUT /api/cars/:id | PUT | Update car listing | Param: id (UUID) Body: { brand?, model?, year?, fuel_type?, transmission?, price_per_day?, deposit?, description?, address?, lat?, lng? } | { id, brand, model, year, price_per_day, deposit, description, address } | Yes (owner) | 200
11 | Car Management | DELETE /api/cars/:id | DELETE | Delete car listing | Param: id (UUID) | { message: 'Car deleted successfully' } | Yes (owner) | 200
12 | Car Management | POST /api/cars/:id/photos | POST | Upload car photos | Param: id (UUID) Body: multipart/form-data: { photos[] (files), sort_order[] } | { photos: [ { id, url, sort_order } ] } | Yes (owner) | 201
13 | Car Management | DELETE /api/cars/:id/photos/:photoId | DELETE | Delete car photo | Params: id (UUID), photoId (UUID) | { message: 'Photo deleted' } | Yes (owner) | 200
14 | Availability | GET /api/cars/:id/availability | GET | Get car availability | Param: id (UUID) Query: date_from?, date_to? | { availability: [ { id, date_from, date_to, type } ] } | No | 200
15 | Availability | POST /api/cars/:id/availability | POST | Set car availability range | Param: id (UUID) Body: { date_from, date_to, type (1=available, 2=blocked) } | { id, car_id, date_from, date_to, type } | Yes (owner) | 201
16 | Availability | DELETE /api/cars/:id/availability/:availId | DELETE | Remove availability entry | Params: id (UUID), availId (UUID) | { message: 'Availability removed' } | Yes (owner) | 200
17 | Bookings | POST /api/bookings | POST | Create booking request | { car_id, start_at (datetime), end_at (datetime) } | { id, car_id, renter_id, start_at, end_at, total_price, deposit_amount, approved: 'PENDING', created_at } | Yes | 201
18 | Bookings | GET /api/bookings | GET | Get all bookings for current user | Query: role? (renter¦owner), status? (PENDING¦APPROVED¦REJECTED¦CANCELLED) | { data: [ { id, car: { id, brand, model }, start_at, end_at, total_price, deposit_amount, approved } ] } | Yes | 200
19 | Bookings | GET /api/bookings/:id | GET | Get single booking details | Param: id (UUID) | { id, car: { id, brand, model, photos }, renter: { id, first_name, avatar_url }, start_at, end_at, total_price, deposit_amount, approved, created_at } | Yes | 200
20 | Bookings | PATCH /api/bookings/:id/approve | PATCH | Approve booking request | Param: id (UUID) | { id, approved: <timestamp>, message: 'Booking approved' } | Yes (owner) | 200
21 | Bookings | PATCH /api/bookings/:id/reject | PATCH | Reject booking request | Param: id (UUID) | { id, approved: 'REJECTED', message: 'Booking rejected' } | Yes (owner) | 200
22 | Bookings | PATCH /api/bookings/:id/cancel | PATCH | Cancel booking (by renter) | Param: id (UUID) | { id, approved: 'CANCELLED', message: 'Booking cancelled' } | Yes (renter) | 200
23 | Reviews | POST /api/reviews | POST | Create a review | { booking_id, rating (1-5), comment?, type (1=car_review, 2=renter_review), car_id? } | { id, booking_id, author_id, car_id, rating, comment, type, created_at } | Yes | 201
24 | Reviews | GET /api/cars/:id/reviews | GET | Get all reviews for a car | Param: id (UUID) Query: page?, limit? | { data: [ { id, rating, comment, author: { first_name, avatar_url }, created_at } ], avg_rating, total } | No | 200
25 | Reviews | GET /api/users/:id/reviews | GET | Get all reviews for a user | Param: id (UUID) Query: type? (1=car, 2=renter), page?, limit? | { data: [ { id, rating, comment, author: { first_name, avatar_url }, type, created_at } ], avg_rating, total } | No | 200
26 | Admin | GET /api/admin/users | GET | List all users (admin) | Query: page?, limit?, is_blocked? | { data: [ { id, email, first_name, last_name, phone, is_blocked, created_at } ], total } | Yes (admin) | 200
27 | Admin | PATCH /api/admin/users/:id/block | PATCH | Block a user (admin) | Param: id (UUID) | { id, is_blocked: true, message: 'User blocked' } | Yes (admin) | 200
28 | Admin | PATCH /api/admin/users/:id/unblock | PATCH | Unblock a user (admin) | Param: id (UUID) | { id, is_blocked: false, message: 'User unblocked' } | Yes (admin) | 200
29 | Admin | GET /api/admin/bookings | GET | List all bookings (admin) | Query: page?, limit?, status? | { data: [ { id, car, renter, start_at, end_at, total_price, approved } ], total } | Yes (admin) | 200

## Legend
LEGEND
Epic Colors
Authentication
Car Management
Availability
Bookings
Reviews
Admin
Priority Colors
Must Have
Should Have
Could Have